## Guidance
Instructions & Scenario Walkthrough
The following is a guide for completing, maintaining, and interpreting the Speak-Up and Anti-Retalization Program for your organization.
Step-by-Step Instructions:
1 | How to use this file:
- Review each Practice Element and confirm the Category and Owner.
- Select Evidence Present (Yes/No/Unsure) and describe any Gaps and 30-Day Fixes.
- Enter Impact, Likelihood, and Complexity to calculate Risk Score and Priority Level.
- Update Status, % Complete, and key dates as work progresses.
2 | Key Fields:
- Category: Program area (e.g., Reporting Channels, Training, Case Management, Anti-Retaliation, Governance).
- Maturity Score (0–5): Level of design and operating effectiveness.
- Risk Score: Auto-calculated (Impact × Likelihood).
- Priority Level: Auto-assigned (High/Medium/Low).
- Status: Not Started, In Progress, On Hold, Complete, N/A.
- RAG Status: Auto-generated based on % Complete.
- For each stakeholder, complete Interest/Concern and Likely Reaction.
3 | Tips for Effective Use:
- Update the assessment at least quarterly.
- Be honest and evidence-based when scoring.
- Use the tool to support discussions with leadership and the Audit Committee.
- Focus first on High Priority items to reduce risk and strengthen the speak-up culture.
Disclaimer:
The information provided in this training session and accompanying handouts is for educational purposes only. While every effort has been made to ensure the accuracy and completeness of the content, the presenter assumes no responsibility for errors, omissions, or any outcomes related to the application of the information provided. Participants are encouraged to seek professional advice or consult relevant guidelines for specific situations.

## Speak-Up Assessment
Speak-Up & Anti-Retaliation Program Mini-Assessment
Use this tool to evaluate whether your organization has effective mechanisms for employees and stakeholders to speak up, report ethical concerns, and be protected from retaliation.
• Review each practice element and select the appropriate Category and Evidence Present (Yes / No / Unsure).
• Complete the fields for Gap, 30-Day Fix, Owner, Dates, % Complete, and other relevant information.
• Enter Impact, Likelihood, and Complexity to automatically calculate Risk Score, Priority Level, and RAG Status.
• Update Status (Not Started / In Progress / On Hold / Complete / N/A) as work progresses.
Practice Element | Category | Evidence Present? (Y/N) | Owner | Gap | 30-Day Fix | Metric | Maturity Score (0–5) | Impact (1–5) | Likelihood (1–5) | Risk Score | Priority Level | Complexity (1–5) | Risk Rating (H/M/L) | Date Assigned | Target Completion Date | % Complete | RAG Status | Status
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started
[11 empty] | High Priority | [5 empty] | Red | Not Started

## Example
Practice Element | Category | Evidence Present? (Y/N) | Owner | Gap | 30-Day Fix | Metric | Maturity Score (0–5) | Impact (1–5) | Likelihood (1–5) | Risk Score | Priority Level | Complexity (1–5) | Risk Rating (H/M/L) | Date Assigned | Target Completion Date | % Complete | RAG Status | Status
Hotline SLA tested | Reporting Channels & Accessibility | No | HR | SLA not tested in past 12 months | Conduct test + document times | Time-to-first-contact <2 days | 1 | 4 | 4 | 16 | High Priority | 2 | High | 2025-02-01 | 2025-03-01 | 0% | Red | Not Started
Escalation protocol published | Intake, Triage & Case Management | Unsure | CAE | Draft exists; not approved | Finalize + communicate | 100% escalations follow protocol | 2 | 3 | 3 | 9 | Medium Priority | 3 | Medium | 2025-01-15 | 2025-03-15 | 40% | Yellow | In Progress
Exception analytics coverage | Risk Assessments & Monitoring | Yes | Internal Audit | Only AP/T&E included | Expand to P-Card + O2C | ≥80% process coverage | 3 | 4 | 4 | 16 | High Priority | 3 | Low | 2025-01-20 | 2025-04-01 | 60% | Yellow | In Progress
Scenario-based ethics training | Awareness, Training & Communication | No | Learning & Development | No cases built | Create 1 case per function | 90% completion rate | 1 | 3 | 3 | 9 | Medium Priority | 4 | High | 2025-02-10 | 2025-05-01 | 0% | Red | Not Started
Speak-up policy updated | Policies, Procedures & Documentation | Yes | Legal | Not reviewed in 18 months | Refresh & circulate | Annual review completed | 4 | 2 | 2 | 4 | Low Priority | 2 | Low | 2024-11-20 | 2025-01-15 | 100% | Green | Complete
Retaliation monitoring process | Anti-Retaliation Controls & Protections | Unsure | HR | No formal tracking | Add tracking field in system | Zero substantiated retaliation | 2 | 5 | 5 | 25 | High Priority | 3 | Medium | 2024-12-01 | 2025-04-15 | 20% | Red | In Progress
Culture survey includes speak-up | Culture, Leadership & Psychosocial Safety | Yes | Compliance | Questions outdated | Add 3 new speak-up items | ≥70% positive response | 3 | 3 | 3 | 9 | Medium Priority | 2 | Low | 2025-01-10 | 2025-03-30 | 50% | Yellow | In Progress
Manager guidance on retaliation | Anti-Retaliation Controls & Protections | No | HR | No one-pager exists | Publish guidance doc | 100% managers trained | 1 | 5 | 5 | 25 | High Priority | 2 | High | 2025-02-05 | 2025-04-05 | 0% | Red | Not Started
Quarterly AC reporting | Governance, Oversight & Reporting | Yes | CAE | Trends not included | Add trending analysis | Quarterly reporting delivered | 4 | 2 | 2 | 4 | Low Priority | 3 | Low | 2024-10-01 | 2024-12-31 | 100% | Green | Complete
Multilingual hotline access | Reporting Channels & Accessibility | Unsure | Compliance | Only English available | Add French and German for Regional Offices | Hotline available in multiple languages | 2 | 4 | 4 | 16 | High Priority | 3 | Medium | 2025-01-18 | 2025-04-18 | 50% | Yellow | In Progress